## Sheet1
Date | Section | Entry
2025-11-03 | ✅ Completed | One Application used by RPG, to decide cut off of SBI/RRB, was not running from Friday. Fixed the issues and make the application live again. Informed Rushikesh to check whether everything is going perfect or not.
2025-11-03 | ✅ Completed | Medical expenses Reimbursement claim windows are enabled by system, but email triggered is failed. Manually sending the email to each one and after that fixation of the issues which caused for either email was not triggered or blank email was triggered.
2025-11-03 | ✅ Completed | In Alternateauthority module, At present alternate authority list is showing based the grade of authority, as previously said by Administration department. With that logic when admin is going to set alternate of Dipika Madam(In Grade H), In the alternate list Name of Priya Madam (In Grade G) was missing. Patch to the HRMS Module to bring all division Head in the List of Alternate List.
2025-11-03 | ✅ Completed | Marge main HRMS code with Prachi and resolve conflicts, test and published.
2025-11-03 | ✅ Completed | Modify procedure of pending list of Employees in Production DB.
2025-11-03 | ✅ Completed | Found Email sending issues in HRMS Profile from Database Email Profile and bring this to the notice of respective authorities.
2025-11-03 | ✅ Completed | Issue in HRMS, regarding employees Type changed and grade changed was detected at the time of testing, is solved and published to the live.
2025-11-03 | ✅ Completed | Provide details of Contractual Employees Salary to the Admin Section , for review purpose.
2025-11-03 | 🧠 Learnings / Notes | Sendig Email from server will monitor tomorrow with IT team.
2025-11-04 | ✅ Completed | Add three candidates data, provided by APG group, in UNFAIRMEANS candidate list.
2025-11-04 | ✅ Completed | Fixation of issue of bulk email triggered. Compliance with solution provided by IT team.
2025-11-04 | 🔃 In Progress | Modify Project Initialization API Flow and corrosponding adjustment in database procedure Is in progress.
2025-11-04 | 🧠 Learnings / Notes | Brainstorming with Prachi , regarding new enhancement of HRMS, requested by Admin. It is regarding Grade Pay Level of Regular Employee and Term and associated consolidated pay of Contractual employees. Admin Suggestion will incorporated by Prachi in HRMS. I help her to understand the logic and database changes regarding development.
2025-11-04 | 🧠 Learnings / Notes | Address Prachi's query regarding a DB procedure Loan EMI transaction of Loan Module.
2025-11-06 | ✅ Completed | Created new procedure to insert Loan EMI Transactions into EMI tables. Initially It Recreates all the application prsent in different tables when ever procedure runs. Now I have created another procedure which take application id and loan subtype id and create EMI transaction for only that specific appliaction of that specific loan sub type. It has scope further enhancement whicha has been shared with prachi. Also helped prachi on some regarding some code.
2025-11-06 | ✅ Completed | Incorporated Window closing information in the mail which triggered during creation of window of medical reimbursement for employees.
2025-11-06 | ✅ Completed | Solved an issue in HRMS, reported by Joel Sir, regarding Leave and Leave Exception.
2025-11-06 | ✅ Completed | Created table and procedure for the tbl_final_project_initiation.
2025-11-06 | ✅ Completed | Modify the batching process of project initiation.
2025-11-06 | ✅ Completed | Make some field non-editable in project initial config tab.
2025-11-07 | ✅ Completed | Modifying Batch, First Project Initiation, Project Initial configuration Drafting, Batch histroy tables and respective procedures.
2025-11-07 | ✅ Completed | Created view for gathering data of those tables.
2025-11-07 | ✅ Completed | Saved data to databases with newly modified/created tables or procedures.
2025-11-07 | 🔃 In Progress | Working Project initial configuartion edit stage i.e after save the data on the database of the initial configuration we will call the same data from the database and after that it will goes to edit stage for further save.
2025-11-07 | 🧠 Learnings / Notes | knowledge transfer session with Prachi on ViewComponent implementation and usage.
2025-11-10 | ✅ Completed | In HRMS, find pending employee who are yet to claim reimbursement of the medical expenses and mail it to the account team. It is requested by Laxmi Madam from accounts team.
2025-11-10 | 🔃 In Progress | Front-end integration of maker and checker activity.
2025-11-10 | 🧠 Learnings / Notes | Knowledge Transfer to Iram and Viswaja regarding Alternate Authority implementation in ACE application.
2025-11-11 | ✅ Completed | Procedure and API creation for ACE application in HRMS.
2025-11-11 | 🔃 In Progress | Working on the editing, send to checker and corrsoponding status modification of a project. Also simultaniously creating preview of what has actually changed in the file.
2025-11-11 | 🔃 In Progress | Working on Creting batch when a batch has ended its life cycle.
2025-11-11 | 🧠 Learnings / Notes | Brainstorming with ACE team for creataion, consumption and implementation of newly ceated API of HRMS and also asked for An API from them to integrate in Dashboard PendingList.
2025-11-12 | ✅ Completed | "Send to Checker" and "Checker Action " batch wise has been completed.
2025-11-12 | ✅ Completed | What has changed by two different version as been developed. When Approver going to take action, a detailed view of changes have been showed to them.
2025-11-12 | 🔃 In Progress | Creating new batch on edit after approval,
2025-11-12 | 🔃 In Progress | Editing of the existing batch.
2025-11-13 | ✅ Completed | Editing of the existing batch.
2025-11-14 | ✅ Completed | Creating new batch on edit after approval
2025-11-14 | ✅ Completed | Fixed error on creation of new project after introducing batch
2025-11-14 | ✅ Completed | Created New API for ACE, Provide All activated Alternate authority and respective Authorities on whoes behalf they are acting as alternate.
2025-11-14 | ✅ Completed | Display project details of any version in IPMS . It will highlight differences from there last version.
2025-11-14 | 🧠 Learnings / Notes | Project review meeting of IPMS has been done. 1. Registration Start Date and End date should be captured. 2. CR meeting on 19-11-2025, will be scheduled. 3. We are not going to include RPG , right now. It will be discussed later. 4. Decision will be gathered from CR about when Project will be finalise i.e when application barred user to modify details. On finalise we will build our master database for future references.
2025-11-14 | 🧠 Learnings / Notes | Provide help in ACE Enhancement also in Payroll Projection.
2025-11-17 | ✅ Completed | Provide solution for swipe mismatch change request, raised on 14-11-2025, by HR/Admin.
2025-11-17 | ✅ Completed | Modifying API as per recruirement from ACE.
2025-11-17 | ✅ Completed | Make provision to show Pending list of ACE application in HRMS dashboard pop-up window. API should be given by ACE team.
2025-11-17 | ✅ Completed | HRMS Branch marging, Procedure and table column transfer from Dev To Prod Server, and publishing of HRMS.
2025-11-17 | 🔃 In Progress | Project Number Details and Post and Specialization under Project No modification in IPMS.
2025-11-17 | 🔃 In Progress | Fixing Redirection of ACE Application URL in HRMS.
2025-11-18 | ✅ Completed | Fix Redirection of ACE Application URL in HRMS.
2025-11-18 | ✅ Completed | Fix issues after implementation of ACE pending list in HRMS, in production.
2025-11-18 | ✅ Completed | Created Logic of CO encashment for tax projection calculation and shared with Prachi.
2025-11-18 | 🔃 In Progress | Project Number Details and Post and Specialization under Project No modification in IPMS.
2025-11-19 | ✅ Completed | Project Number Details and Post and Specialization under Project No modification in IPMS.
2025-11-19 | 🧠 Learnings / Notes | IPMS meeting with CR has been done. 1. In the detail view, they suggested to show version number along with checker name and date. 1. Asked for a non-editable Description field at the time of project initiation. 1. They asked for a specific header like Initial Project or Revised Project, along with revision date and approver name, to indicate the project status. 1. They have a requirement of trail mail configuration in the application; i.e., when a mail is triggered after the first time, it should contain all previous emails of the project. 1. In the next patch, we propose to provide the following: 1. Project numbers with post and specialization details entry. 2. Assign permanent project numbers. 3. Configure email recipients (to whom the email will be triggered). 4. Send email for specific mention, if required, to groups or individuals. 5. Accommodate user-category-wise login for visualization of flow of data. 6. Also try to integrate full project details rendered as view.
2025-11-19 | 🚧 Blockers | a. Project Numbers with post and specialization details entry. b. Assign permanent project numbers. c. Configure email, i.e. to whom the email will be triggered. d. Send email to for a specific mention , if required, to specific group of people or individuals. e. We will try to accomodate user category wise login for visualization of flow
2025-11-20 | ✅ Completed | Creataion and updation of Project Number Details and Post & Specialization under Project No(s) has been done.
2025-11-20 | 🔃 In Progress | Assigning Premament Project numbers.
2025-11-20 | 🔃 In Progress | Show modfied details of Project Number, Post and Specializations are going on.
2025-11-20 | 🧠 Learnings / Notes | IPMS meeting with CR was held on 19th Novermebr, 2025. Following points are highlight of the discussion during the presentation. 1. In the detail view, they suggested to show version number along with checker name and date. 1. Asked for a non-editable Description field at the time of project initiation. 1. They asked for a specific header like Initial Project or Revised Project, along with revision date and approver name, to indicate the project status. 1. They have a requirement of trail mail configuration in the application; i.e., when a mail is triggered after the first time, it should contain all previous emails of the project. 1. In the next patch, we propose to provide the following: 1. Project numbers with post and specialization details entry. 2. Assign permanent project numbers. 3. Configure email recipients (to whom the email will be triggered). 4. Send email for specific mention, if required, to groups or individuals. 5. Accommodate user-category-wise login for visualization of flow of data. 6. Also try to integrate full project details rendered as view.
2025-11-20 | 🚧 Blockers | Increasing and Decreasing of Project number in initial configuration , will create problems. Need to fix the area.
2025-11-21 | ✅ Completed | Resolve problem in perquisite of the HRR data creation and fetching.
2025-11-21 | 🔃 In Progress | Assiging of Project Numbers to the project is going on. Resolve issue with displaying fields to the views.
2025-11-21 | 🧠 Learnings / Notes | Scheduled meeting with Director Sir and other stakeholders regarding Nominee application, Asset and Liabilities and Payroll.
2025-11-24 | ✅ Completed | Provide solution regarding employee retirement issue,
2025-11-24 | ✅ Completed | In the detail view, CR suggested to show version number along with checker name and date. It is Incorporated.
2025-11-24 | 🔃 In Progress | Working on assign Project numbers and confirm projects. Procedure created. evaluating on various cases that may have arises.
2025-11-25 | 🔃 In Progress | Creation of history of project numbers confirmed, postponed and removed.
2025-11-25 | 🔃 In Progress | Provide solution for creation of activity of single as well as selected projects to assign project numbers, postpone of a project and deletion of a project.
2025-11-26 | 🔃 In Progress | Working with same Project Number Tab. Alteration of Project number assign part, as Bring post and specialization details to the list for the user to understand for the kaing of decision.
2025-11-28 | ✅ Completed | Single Project Creation has been done. Working on fixing taken on multiple project number at a time.